## Unique Bugs
UPTRUE QA — Unique Bug Report (Consolidated)
Total Unique Bugs: 129 ¦ Sources: Rahul Yadav · Shorya Kumar · Sourav Naugain · Kriti Chawla
S.No | Unique Bug ID | Original Bug ID | Bug Title | Bug Description | Type / Module | Priority | Steps to Reproduce | Expected Result | Actual Result | Environment | Reported By
1 | UB_001 | B_001 | Suggestion - Add “Back to Top” (Up Arrow) button for better UX | Suggestion - for better UX, we can give a provision to navigate on top of screen rather than to scroll up for few sec. Up arrow button | UI Enhancement | Medium | 1. Open homepage 2. Scroll to footer | A visible “Back to Top” button should be present at bottom-right and scroll user to top on click | No “Back to Top” button present in footer or page | https://dev.uptrue.io/ | Rahul Yadav
2 | UB_002 | B_002 | Clicking site logo does not navigate to top of homepage | When user is on homepage URL, and clicks on site logo. system does not navigate to top of landing page | Functional | Medium | 1. Open homepage 2. Click on site logo | User should be navigated to top of homepage | The base URL of site is on site icon in footer however it's not navigating to top of page. | https://dev.uptrue.io/ | Rahul Yadav
3 | UB_003 | B_003 | Missing favicon for site identity | Missing site favicon(favorite icon), need to added for identity of site | UI | High | 1. Open site in browser 2. Check tab icon | Favicon (16x16 px) should be visible in browser tab | Favicon is missing | https://dev.uptrue.io/ | Rahul Yadav
4 | UB_004 | B_004 | No hover/glow effect on active items | Live- On hover there should be glowing effect on active items. | UI Enhancement | Medium | 1. Hover over service items | Items should have glowing/hover effect for better UX | There is no hover effect on all services | https://dev.uptrue.io/ | Rahul Yadav
5 | UB_005 | B_005 | LIVE tag shows outdated data (70 hrs ago) | Live - Live systems appear dynamic (not static) to recognize user instantly real-time data, to get trust of user on monitoring system | Functional/UI | High | 1. Open Live section 2. Observe timestamps | LIVE section should show real-time/dynamic data | Currently observed that showing a 70 hr ago for all services. Confusing with “LIVE” tag | https://dev.uptrue.io/ | Rahul Yadav
6 | UB_006 | B_006 | Live section lacks dynamic indicators (pulsing badges) | Live section - From the UI, I observed that the live section uses static indicators. I suggested adding pulsing live badges to better communicate real-time activity and improve user awareness. | UI Enhancement | Medium | 1. Open Live section | Live indicators should be dynamic (pulsing/animated) | Static indicators used | https://dev.uptrue.io/ | Rahul Yadav
7 | UB_007 | B_007 | 404 Error page missing for invalid URLs | 404 Error Page is Missing for Invalid URL on Website. Note: 404 page helps users recover from errors, improves UX, and ensures proper SEO and error handling.” | Functional | High | 1. Enter invalid URL2. Press Enter | Custom 404 page with message, navigation & branding | No proper 404 page displayed | https://dev.uptrue.io/ | Rahul Yadav
8 | UB_008 | B_008 | Leaderboard page loads slowly due to heavy API response | leaderboard page taking more time to load, as API response is too high. | Performance | High | 1. Open URL 2. Check Network tab 3. Observe response time | Page should load within acceptable time (<3 sec) | Page load is slow due to high API response time | https://dev.uptrue.io/ | Rahul Yadav
9 | UB_009 | B_009 | Footer leaderboard link slow/inaccessible | Footer - Leaderboard page is slow to load and inaccessible via Footer navigation due to API delay and broken link | Functional | High | 1. Click leaderboard from footer | Page should open quickly via footer link | Slow loading / sometimes inaccessible | https://dev.uptrue.io/ | Rahul Yadav
10 | UB_010 | B_010 | Carousel progress bar not draggable | carousel-progress is not draggable. not functioning | Functional | Medium | 1. Open section 2. Try dragging carousel progress | Progress bar should be draggable | Not draggable / not functioning | https://dev.uptrue.io/ | Rahul Yadav
11 | UB_011 | B_011 | ‘See How It Works’ CTA missing icon | UI inconsistency observed as ‘See How It Works’ CTA lacks icon unlike adjacent action buttons | UI | Low | 1. Compare CTA buttons | CTA should have consistent icon like others | Icon missing causing UI inconsistency | https://dev.uptrue.io/ | Rahul Yadav
12 | UB_012 | B_012 | Low contrast font on dark background | Need to change the font colour as in dark background the opacity of is low | UI | Medium | 1. Observe text on dark UI | Text should have proper contrast for readability | Font opacity too low, hard to read | https://dev.uptrue.io/ | Rahul Yadav
13 | UB_013 | B_013 | Missing space between text and hyperlink (cookies page) | Need to keep space between copy "our and privacy policy" hyperlink text | UI | Low | 1. Open page 2. Check text spacing | Proper spacing between text and links | No spacing observed | https://dev.uptrue.io/ | Rahul Yadav
14 | UB_014 | B_015 | Email not clickable (mailto missing) | " privacy@uptrue.io" it should be hyperlink to open the mailto for great user experience | UI | Low | 1. Open page 2. Click email | Emails should open mail client | Not clickable | https://dev.uptrue.io/ | Rahul Yadav
15 | UB_015 | B_016 | Spacing issues (text & links) | Need to keep space between copy " see our" and Cookie Policy." hyperlink text | Functional | Medium | 1. Open pages 2. Check text | there should be space between text and hyperlink text | No spacing observed | https://dev.uptrue.io/ | Rahul Yadav
16 | UB_016 | B_019 | The label name message is missing in object BODY | Contact us - In payload/request body, the label name message is missing in object BODY | UI | Low |  |  |  | https://dev.uptrue.io/ | Rahul Yadav
17 | UB_017 | B_020 | Contact us form not submitting | Contact us- User not able to submit the contact us form, as getting an error. verify the network tab attached screenshot | Functional | High | 1. Enter all required form details 2. Submit form | Form should be submitted successfully | User not able to submit the contact us form | https://dev.uptrue.io/ | Rahul Yadav
18 | UB_018 | B_022 | Blog newsletter form not submitting | Blog- User not able to submit the "news letter" form, as getting an error. verify the network tab attached screenshot | Functional | High |  | Newsletter should be submitted successfully | Error observed (network failure) | https://dev.uptrue.io/ | Rahul Yadav
19 | UB_019 | B_023 | There should be informational message similar to "incident report". if there is no data | There should be informational message similar to "incident report". if there is no data | [6 empty] | Rahul Yadav
20 | UB_020 | B_024 | UI distorted in mobile view | Responsive - Mobile view- The real cost of downtime section CTA and cards truncating from right of screen. need to manage styling for mobile view (375*812) | UI | Low |  | Should align properly from left | Misaligned dropdown | https://dev.uptrue.io/ | Rahul Yadav
21 | UB_021 | B_025 | Missing company number | Terms Page - As per specification, Missing the company number under contact us details. | UI | Medium |  |  |  | https://dev.uptrue.io/ | Rahul Yadav
22 | UB_022 | B_026 | Broken image | Broken image for public status/test page | UI | Low |  |  |  | https://dev.uptrue.io/ | Rahul Yadav
23 | UB_023 | B_027 | Status Page- Getting an error "Something went wrong. Please try again." | Status Page- Getting an error "Something went wrong. Please try again." | Functional | High | 1. Open status page 2. Enter email to submit newsletter 3. Click on submit button | Newsletter should be submitted successfully | Error observed (network failure) | https://dev.uptrue.io/ | Rahul Yadav
24 | UB_024 | B_028 | Alignment issue | Dropdown field should be aligned from left | UI | Low |  | It should be aligned for good UX | Not aligned | https://dev.uptrue.io/ | Rahul Yadav
25 | UB_025 | B_029 | UI distorted | Need to manage the styling of search box | UI | Low |  | It should be aligned for good UX | Not aligned in mobile view | https://dev.uptrue.io/ | Rahul Yadav
26 | UB_026 | B_030 | Getting an error - API access is not available | Generate API key - getting an error - API access is not available on your current plan. Please upgrade | Functional | High |  | API key should be accesable for subscribed user | API access is not available on your current plan. Please upgrade | https://dev.uptrue.io/ | Rahul Yadav
27 | UB_027 | B_031 | Competitor added. First uptime check not runs. | Competitor added. First uptime check not runs. | Functional | High |  | First uptime check should be run | First uptime check not runs. | https://dev.uptrue.io/ | Rahul Yadav
28 | UB_028 | B_01 | The Leaderboard link does not respond when clicked. The Help Center, API Docs, and Status links redirect users to the login page if they are not logged in. If the user is already logged in, clicking these links results in a 404 (Page Not Found) error instead of loading the respective pages. | The Leaderboard link does not respond when clicked. The Help Center, API Docs, and Status links redirect users to the login page if they are not logged in. If the user is already logged in, clicking these links results in a 404 (Page Not Found) error instead of loading the respective pages. |  | Medium | 1)Open the application (logged out / normal browser state) 2)Scroll to Footer section 3)Click each footer link one by one: Leaderboard Help Centre API Docs Status | All links navigate correctly. No 404s. Legal pages open. | Leaderboard link is not responding on click. Help Center, API Docs, and Status links redirect to the login page for logged-out users, and show a 404 (Page Not Found) error for already logged-in users. | Dev | Shorya Kumar
29 | UB_029 | B_02 | When a blog post is opened, the text content loads correctly but images do not appear, indicating an issue with image loading or rendering. Additionally, on the “All Posts” page, the “Load More Articles” button does not function properly—it scrolls the page to the top instead of loading new posts, which breaks the pagination/infinite scroll experience and negatively impacts user experience. | When a blog post is opened, the text content loads correctly but images do not appear, indicating an issue with image loading or rendering. Additionally, on the “All Posts” page, the “Load More Articles” button does not function properly—it scrolls the page to the top instead of loading new posts, which breaks the pagination/infinite scroll experience and negatively impacts user experience. |  | Medium | 1)Open the application (logged out / normal browser state) 2)Naviagte to blog section 3)Click on each blog post > Click on load more article to observe the pagination issue | Blog posts listed. Feature images visible. No broken layout. | Blog post content loads on click but images are missing. “Load More Articles” is displayed, but clicking it does not load new posts and redirects to the top of the page. | Dev | Shorya Kumar
30 | UB_030 | B_03 | This is a valid issue because the status page is not loading at all. Instead of showing the “All systems operational” banner, the user is redirected to the signup page or sees a 404 error when already logged in. This prevents users from accessing the status information, meaning the main functionality of the page is not working. | This is a valid issue because the status page is not loading at all. Instead of showing the “All systems operational” banner, the user is redirected to the signup page or sees a 404 error when already logged in. This prevents users from accessing the status information, meaning the main functionality of the page is not working. |  | High | 1) In public page , scroll down to footer 2) click on status link before login and after login | Green "All systems operational" banner shown at top. | The “All systems operational” banner is not displayed. When the user clicks on the status page, they are redirected to the signup page, and if already logged in, a 404 error is shown instead of loading the status page. | Dev | Shorya Kumar
31 | UB_031 | B_04 | This is a valid issue because the incident details are not visible to the user. Instead of showing the incident title, start time, and timeline, the status page is not loading and redirects to the signup page or shows a 404 error. This blocks users from viewing important incident information, meaning the core functionality of the status page is not working properly. | This is a valid issue because the incident details are not visible to the user. Instead of showing the incident title, start time, and timeline, the status page is not loading and redirects to the signup page or shows a 404 error. This blocks users from viewing important incident information, meaning the core functionality of the status page is not working properly. |  | High | 1) In public page , scroll down to footer 2) click on status link before login and after login | Incident shown with title, start time, and timeline. | The incident details are not displayed. When the user clicks on the status page, they are redirected to the signup page, and if already logged in, a 404 error is shown instead of loading the incident information with title, start time, and timeline. | Dev | Shorya Kumar
32 | UB_032 | B_05 | This is a valid issue because the status page is not working as expected. Instead of showing uptime bars for different time ranges, the page does not load properly. Users are either redirected to the signup page or see a 404 error even when logged in. This prevents access to uptime information and shows that the page routing or access handling is broken. | This is a valid issue because the status page is not working as expected. Instead of showing uptime bars for different time ranges, the page does not load properly. Users are either redirected to the signup page or see a 404 error even when logged in. This prevents access to uptime information and shows that the page routing or access handling is broken. |  | High | 1) In public page , scroll down to footer 2) click on status link before login and after login | Uptime bars update for each time range. No crash. | The uptime bars are not displayed or updated for any time range. When the user clicks on the status page, they are redirected to the signup page, and if already logged in, a 404 error is shown instead of loading the uptime data. | Dev | Shorya Kumar
33 | UB_033 | B_06 | This is a valid issue because the status page is not working properly. Instead of showing the confirmation message, the user is redirected to the signup page, and if already logged in, a 404 error is shown. This means the page is not loading correctly and the expected action is not completed. | This is a valid issue because the status page is not working properly. Instead of showing the confirmation message, the user is redirected to the signup page, and if already logged in, a 404 error is shown. This means the page is not loading correctly and the expected action is not completed. |  | Medium | 1) In public page , scroll down to footer 2) click on status link before login and after login | Confirmation message shown. No page reload error. | The confirmation message is not shown and the page does not behave as expected. When the user clicks on the status page, they are redirected to the signup page, and if already logged in, a 404 error is displayed instead of showing the confirmation message. | Dev | Shorya Kumar
34 | UB_034 | B_07 | This is a valid issue because the system is not showing the proper validation error when a subscription is not created. Instead of displaying a clear message, the status page does not load correctly. Users are redirected to the signup page, and if already logged in, they see a 404 error. This means the error handling flow is broken and the expected validation behavior is not working. | This is a valid issue because the system is not showing the proper validation error when a subscription is not created. Instead of displaying a clear message, the status page does not load correctly. Users are redirected to the signup page, and if already logged in, they see a 404 error. This means the error handling flow is broken and the expected validation behavior is not working. |  | Medium | 1) In public page , scroll down to footer 2) click on status link before login and after login | Validation error shown. No subscription created. No crash. | The validation error is not shown and no proper message is displayed. When the user clicks on the status page, they are redirected to the signup page, and if already logged in, a 404 error appears instead of showing the validation error. | Dev | Shorya Kumar
35 | UB_035 | B_09 | This is a valid issue because the system is not handling the second subscription properly. Instead of showing a smooth response without errors, the status page does not load correctly. Users are either redirected to the signup page or get a 404 error even when logged in. This shows that the flow is broken and the expected behavior is not working. | This is a valid issue because the system is not handling the second subscription properly. Instead of showing a smooth response without errors, the status page does not load correctly. Users are either redirected to the signup page or get a 404 error even when logged in. This shows that the flow is broken and the expected behavior is not working. |  | Low | 1) In public page , scroll down to footer 2) click on status link before login and after login | Second subscription handled gracefully. No duplicate. No crash. | The second subscription is not handled properly. Instead of a graceful response, the status page redirects to the signup page, and if the user is already logged in, a 404 error is shown. No proper handling message is displayed, and the page fails to load correctly. | Dev | Shorya Kumar
36 | UB_036 | B_10 | This is a valid issue because the status page is not loading correctly. Instead of handling the request properly and showing the correct page (or a proper 404 page in all cases), users are sometimes redirected to the signup page and sometimes get a 404 error even when logged in. This shows inconsistent routing and broken page access, which prevents the expected behavior from working. | This is a valid issue because the status page is not loading correctly. Instead of handling the request properly and showing the correct page (or a proper 404 page in all cases), users are sometimes redirected to the signup page and sometimes get a 404 error even when logged in. This shows inconsistent routing and broken page access, which prevents the expected behavior from working. |  | Medium | 1) In public page , scroll down to footer 2) click on status link before login and after login | 404 page shown. Not a blank page or server error. | The 404 page is not consistently shown as expected. When the user clicks on the status page, they are redirected to the signup page, and if already logged in, a 404 error is displayed instead of a proper status page load without errors. | Dev | Shorya Kumar
37 | UB_037 | B_11 | This is a valid issue because the status page is not opening correctly. Instead of showing a fully responsive page with uptime bars and a working subscribe form, users are redirected to the signup page. Even when the user is already logged in, a 404 error is shown. This means the page is not accessible, and the main features of the status page are not available, showing a broken or incorrect routing behavior. | This is a valid issue because the status page is not opening correctly. Instead of showing a fully responsive page with uptime bars and a working subscribe form, users are redirected to the signup page. Even when the user is already logged in, a 404 error is shown. This means the page is not accessible, and the main features of the status page are not available, showing a broken or incorrect routing behavior. |  | Medium | 1) In public page , scroll down to footer 2) click on status link before login and after login | Fully responsive. Uptime bars visible. Subscribe form usable | The page is not loading properly, so responsiveness, uptime bars, and subscribe form are not visible or usable. When the user clicks on the status page, they are redirected to the signup page, and if already logged in, a 404 error is shown instead of the expected status page content. | Dev | Shorya Kumar
38 | UB_038 | B_12 | Magic link email is not sent to the user. Instead, an error message appears: "Failed to send magic link. Please try again," which stops the user from logging in. | Magic link email is not sent to the user. Instead, an error message appears: "Failed to send magic link. Please try again," which stops the user from logging in. |  | High | 1) Go to signup page 2) Enter a new email address 3) Click Send Magic Link | Magic link email received within 60 seconds. Email from Uptrue domain (not Supabase). | Failed to send the magic link. An error message is displayed: "Please try again." | Dev | Shorya Kumar
39 | UB_039 | B_13 | Magic link login is failing, and the system shows an error message: "Failed to send magic link. Please try again." Due to this, users cannot log in using email-based authentication. However, Google sign-up authentication is working correctly and users are successfully logged in and redirected to the dashboard. | Magic link login is failing, and the system shows an error message: "Failed to send magic link. Please try again." Due to this, users cannot log in using email-based authentication. However, Google sign-up authentication is working correctly and users are successfully logged in and redirected to the dashboard. |  | High | 1) Go to signup page 2) Enter a new email address 3) Click Send Magic Link | Logged in and redirected to dashboard. Session active. | When requesting a magic link, an alert message appears: "Failed to send magic link. Please try again," and the login process is not completed. However, the authentication process completes successfully when the user signs up using Google. | Dev | Shorya Kumar
40 | UB_040 | B_17 | Magic link is not being sent to the user. Instead of successfully sending the email and allowing login through the link, the system shows an error message: "Failed to send magic link. Please try again later." As a result, users are unable to log in using the magic link method. | Magic link is not being sent to the user. Instead of successfully sending the email and allowing login through the link, the system shows an error message: "Failed to send magic link. Please try again later." As a result, users are unable to log in using the magic link method. |  | High | 1) Go to signup page 2) Enter a new email address 3) Click Send Magic Link | Magic link sent. On click, logs into existing account (no duplicate org created). | Magic link is not sent, and the system shows an error message: "Failed to send magic link. Please try again later." Login via magic link is not possible. | Dev | Shorya Kumar
41 | UB_041 | B_18 | When a monitor is created successfully, it should display the SSL expiry date on the monitor detail page. However, after creation, the monitor is shown in the list but the SSL expiry date is not visible on the detail page. | When a monitor is created successfully, it should display the SSL expiry date on the monitor detail page. However, after creation, the monitor is shown in the list but the SSL expiry date is not visible on the detail page. |  | High | 1) Login as a User > New monitor → SSL type 2) Enter domain (no https://) 3. Save | Monitor created. Shows SSL expiry date on detail page. | Monitor is created successfully and appears in the system, but the SSL expiry date is not displayed on the detail page. | Dev | Shorya Kumar
42 | UB_042 | B_19 | After successfully creating a monitor, the domain expiry date is not shown on the monitor details page. The monitor is created and visible in the list, but the expected domain expiry information is missing, which affects proper monitoring of domain validity. | After successfully creating a monitor, the domain expiry date is not shown on the monitor details page. The monitor is created and visible in the list, but the expected domain expiry information is missing, which affects proper monitoring of domain validity. |  | High | 1) Login asa a user > New monitor → Domain type 2) Enter domain 3) Save | Monitor created. Shows domain expiry date. | Monitor is created successfully, but the domain expiry date is not displayed. | Dev | Shorya Kumar
43 | UB_043 | B_20 | This is a valid bug because the heartbeat URL should be created and shown after a monitor is created. But here, the monitor is created successfully and still the heartbeat URL is not generated or displayed. This is a missing feature in the process, and without it the monitoring will not work properly. | This is a valid bug because the heartbeat URL should be created and shown after a monitor is created. But here, the monitor is created successfully and still the heartbeat URL is not generated or displayed. This is a missing feature in the process, and without it the monitoring will not work properly. |  | High | 1) Login as a user > New monitor → Heartbeat type 2) Enter name 3) Save | Monitor created. Unique heartbeat URL generated and shown. | Monitor is created successfully, but the unique heartbeat URL is not generated or displayed. | Dev | Shorya Kumar
44 | UB_044 | B_21 | This is a valid bug because the system should check if the URL is correct before creating the monitor. But here, even an invalid URL is accepted and no error message is shown. This means validation is missing. Because of this, wrong data can be saved and monitoring may not work properly. | This is a valid bug because the system should check if the URL is correct before creating the monitor. But here, even an invalid URL is accepted and no error message is shown. This means validation is missing. Because of this, wrong data can be saved and monitoring may not work properly. |  | High | 1) Login asa a user > New monitor → HTTP type 2) Enter "notaurl" in URL field 3) Save | Validation error: invalid URL format. | No validation error is shown for the invalid URL format, and the monitor is created successfully | Dev | Shorya Kumar
45 | UB_045 | B_22 | This is a valid functional/navigation bug because the post-update redirection flow does not match the expected user journey. After successfully updating monitor details, the system should redirect the user back to the monitor list page to maintain consistency and allow easy verification of all monitors in one place. Instead, the user is redirected to the monitor detail page, which breaks the expected navigation flow and creates inconsistency in user experience. This indicates a wrong routing/redirect logic after successful update | This is a valid functional/navigation bug because the post-update redirection flow does not match the expected user journey. After successfully updating monitor details, the system should redirect the user back to the monitor list page to maintain consistency and allow easy verification of all monitors in one place. Instead, the user is redirected to the monitor detail page, which breaks the expected navigation flow and creates inconsistency in user experience. This indicates a wrong routing/redirect logic after successful update |  | High | 1) Login as a user >Open monitor → Edit 2) Change name 3.) Save | User are redirect to the monitors list after monitor details update | After updating monitor details, the user is redirected to the monitor detail page instead of the monitor list page. | Dev | Shorya Kumar
46 | UB_046 | B_23 | This is a valid UI/UX functional bug because the system successfully updates the monitor details but fails to provide any success confirmation to the user. After performing an important action like updating Name or URL, a success message or toast notification is expected to confirm that the changes have been saved. Since no feedback is shown, the user is left uncertain about whether the update was completed successfully. | This is a valid UI/UX functional bug because the system successfully updates the monitor details but fails to provide any success confirmation to the user. After performing an important action like updating Name or URL, a success message or toast notification is expected to confirm that the changes have been saved. Since no feedback is shown, the user is left uncertain about whether the update was completed successfully. |  | Medium | 1) Login as a user > Open monitor → Edit 2) Change name 3) Save > Observe the result | After update monitors details a pop message show: Details update sucessfully | No pop-up or success message is displayed after updating monitor details. | Dev | Shorya Kumar
47 | UB_047 | B_24 | This is a valid functional validation bug with high impact because the system is not enforcing input validation for webhook URLs during channel creation. A webhook URL should be validated before saving to ensure it is correctly formatted and functional. However, the system allows invalid webhook URLs to be saved without any error or warning, indicating a missing frontend and/or backend validation check. | This is a valid functional validation bug with high impact because the system is not enforcing input validation for webhook URLs during channel creation. A webhook URL should be validated before saving to ensure it is correctly formatted and functional. However, the system allows invalid webhook URLs to be saved without any error or warning, indicating a missing frontend and/or backend validation check. |  | Medium | 1) Login as a User > Create webhook channel 2) Enter "notaurl" as URL 3) Save | Validation error. Not saved. | The webhook channel is created successfully even with an invalid URL, and no validation error is shown. | Dev | Shorya Kumar
48 | UB_048 | B_25 | This is a valid UI/UX functional bug because the system completes the delete action successfully but fails to provide user feedback. After performing an important destructive action like deleting an alert channel, a success confirmation message is expected to inform the user that the operation was completed. Since no pop-up or toast message is shown, the user has no clear confirmation of success, which can lead to confusion or repeated actions. This indicates a missing success notification handling in the UI layer, affecting usability and user experience. | This is a valid UI/UX functional bug because the system completes the delete action successfully but fails to provide user feedback. After performing an important destructive action like deleting an alert channel, a success confirmation message is expected to inform the user that the operation was completed. Since no pop-up or toast message is shown, the user has no clear confirmation of success, which can lead to confusion or repeated actions. This indicates a missing success notification handling in the UI layer, affecting usability and user experience. |  | Medium | 1) Login as a User > Open an alert channel 2) Click Delete 3) Confirm | Channel removed . A pop message show channel delete sucessfully | Alert channel is deleted successfully, but no pop-up or success message is shown to confirm the deletion. | Dev | Shorya Kumar
49 | UB_049 | B_26 | This is a valid functional validation bug because the system is missing an important business rule check during status page creation. A status page should require at least one monitor to ensure it displays meaningful and valid data. However, the system allows creation without selecting any monitors and does not show any validation error. This indicates that frontend and/or backend validation is missing or not enforced, resulting in an incomplete status page setup. Due to this, users can create empty or non-functional status pages, which defeats the purpose of the feature and may lead to confusion or incorrect reporting. | This is a valid functional validation bug because the system is missing an important business rule check during status page creation. A status page should require at least one monitor to ensure it displays meaningful and valid data. However, the system allows creation without selecting any monitors and does not show any validation error. This indicates that frontend and/or backend validation is missing or not enforced, resulting in an incomplete status page setup. Due to this, users can create empty or non-functional status pages, which defeats the purpose of the feature and may lead to confusion or incorrect reporting. |  | High | 1) login as a User > Navigate to Status Page > Atleast one Monitor Exist | A validation message shown. Please Select the monitor. | Status page is created successfully even without selecting any monitor, and no validation message is shown. | Dev | Shorya Kumar
50 | UB_050 | B_27 | This is a valid high-severity functional/authorization bug because the system is not enforcing the defined plan limits. The expected behavior is to block the second report generation or show an upgrade/limit message once the user exceeds the allowed quota. | This is a valid high-severity functional/authorization bug because the system is not enforcing the defined plan limits. The expected behavior is to block the second report generation or show an upgrade/limit message once the user exceeds the allowed quota. |  | High | 1) Login as a User > Monitor Exist with Check History | 2nd report blocked. Upgrade prompt or limit message shown. | The report is generated successfully without any restriction. The system does not block the action or show an upgrade prompt, and the report is created and accessible as expected. | Dev | Shorya Kumar
51 | UB_051 | B_28 | This is a valid UI/Functional bug because the system is correctly updating GBP pricing and calculating the annual discount internally, but it is not displaying the savings percentage in the UI. The savings value is an important part of pricing transparency, as users rely on it to compare monthly vs annual plans and make purchase decisions. | This is a valid UI/Functional bug because the system is correctly updating GBP pricing and calculating the annual discount internally, but it is not displaying the savings percentage in the UI. The savings value is an important part of pricing transparency, as users rely on it to compare monthly vs annual plans and make purchase decisions. |  | High | 1) login as a User > Go to billing page 2) Click Monthly / Annual toggle | Prices update for GBP plans. Annual shows savings %. | The GBP pricing is updated correctly and reflects the new values. However, the annual plan does not display the savings percentage. Only the base annual price is shown, and the expected “savings %” label is missing from the UI. | Dev | Shorya Kumar
52 | UB_052 | B_29 | This is a bug because the invoice is expected to show complete billing details (date, amount, and plan name) for proper clarity and record keeping. Since the plan name is missing, users cannot easily identify which subscription plan a specific invoice belongs to, leading to incomplete and unclear billing information. | This is a bug because the invoice is expected to show complete billing details (date, amount, and plan name) for proper clarity and record keeping. Since the plan name is missing, users cannot easily identify which subscription plan a specific invoice belongs to, leading to incomplete and unclear billing information. |  | High | 1) Login as a User > Complete a Stripe payment 2) Check billing page invoices section | Invoice listed with date, amount, plan name. | The invoice list displays the date and amount correctly for each entry. However, the plan name is not shown in the invoice details, resulting in incomplete invoice information for users. | Dev | Shorya Kumar
53 | UB_053 | B_30 | This is a valid UI/UX bug because the invoice PDF should open in a new tab for better user experience. Opening it in the same tab replaces the current page, which can interrupt the user’s flow and force them to navigate back again. This indicates an incorrect link behavior or missing “open in new tab” configuration | This is a valid UI/UX bug because the invoice PDF should open in a new tab for better user experience. Opening it in the same tab replaces the current page, which can interrupt the user’s flow and force them to navigate back again. This indicates an incorrect link behavior or missing “open in new tab” configuration |  | High | 1) Login as a User > Click on an invoice in billing history | Stripe invoice PDF opens in new tab. | Stripe invoice PDF opens in the same (existing) tab instead of opening in a new tab. | Dev | Shorya Kumar
54 | UB_054 | B_31 | This is a valid functional bug because when a user selects “cancel at period end”, the subscription should be marked for cancellation and stay active only until the current billing period ends. But here, the cancellation is not happening, which means the system is not updating the subscription status correctly. This can lead to users being charged or having incorrect access control. | This is a valid functional bug because when a user selects “cancel at period end”, the subscription should be marked for cancellation and stay active only until the current billing period ends. But here, the cancellation is not happening, which means the system is not updating the subscription status correctly. This can lead to users being charged or having incorrect access control. |  | High | 1) login as a User > Go to billing (on paid plan) 2) Click Cancel Plan 3) Confirm > Observe thr result | Subscription set to cancel at period end. Access continues until then. | The subscription is not getting cancelled even after setting it to cancel at period end, and access is not being updated as expected. | Dev | Shorya Kumar
55 | UB_055 | B_32 | This is a valid functional bug because when a user cancels a subscription, the system should either show a cancellation date and keep access until the period ends, or properly update the cancellation status. But here, the subscription is not getting cancelled at all, and the expected cancellation flow is not working. This means the cancellation logic is broken, which can cause incorrect access and billing issues. | This is a valid functional bug because when a user cancels a subscription, the system should either show a cancellation date and keep access until the period ends, or properly update the cancellation status. But here, the subscription is not getting cancelled at all, and the expected cancellation flow is not working. This means the cancellation logic is broken, which can cause incorrect access and billing issues. |  | High | 1) Login as a User > Cancel subscription 2) Check plan features still accessible 3) Check billing page Observe the Result | Shows cancellation date. Features still accessible until period end. | The subscription is not cancelled, and the cancellation date is not applied correctly. Features continue to remain active without proper cancellation handling. | Dev | Shorya Kumar
56 | UB_056 | B_33 | This is a valid payment validation bug because the system should properly validate the card details and show a clear, consistent payment failure message. But here, the payment fails due to an invalid card number error and the expected payment flow (like updating status to past_due and notifying the user) is not completed. This indicates that the payment process is not handled correctly, which can lead to failed transactions and poor user experience. | This is a valid payment validation bug because the system should properly validate the card details and show a clear, consistent payment failure message. But here, the payment fails due to an invalid card number error and the expected payment flow (like updating status to past_due and notifying the user) is not completed. This indicates that the payment process is not handled correctly, which can lead to failed transactions and poor user experience. |  | High | 1) login as a User > Setting > billing > Use Stripe test card: 4000 0000 0000 9995 2. Complete checkout > Observe the Result | Payment fails. Subscription status shows as past_due. User notified. | During payment, the system shows an “invalid card number” error, and the payment is not processed. | Dev | Shorya Kumar
57 | UB_057 | B_34 | This is a valid functional bug because when a user cancels a subscription, the system should update the subscription status and schedule it to revert to the Free plan at the end of the current billing period. However, in this case, the cancellation is not happening, and the subscription remains active. This indicates that the cancellation logic or billing status update is not working correctly, which can lead to incorrect access control and billing issues. | This is a valid functional bug because when a user cancels a subscription, the system should update the subscription status and schedule it to revert to the Free plan at the end of the current billing period. However, in this case, the cancellation is not happening, and the subscription remains active. This indicates that the cancellation logic or billing status update is not working correctly, which can lead to incorrect access control and billing issues. |  | High | 1) Login as a User > INR user on paid plan → billing page 2) Click Cancel 3) Confirm (two-step) > Observe the result | Subscription cancelled. Reverts to Free at end of current period. | Subscription is not cancelled, and it does not revert to the Free plan at the end of the current period | Dev | Shorya Kumar
58 | UB_058 | B_35 | This is a valid bug because even though the organization name is updated successfully in the system, the updated value is not immediately reflected in all parts of the application. After the update, some sections like other tabs and the dashboard header still show the old organization name. The correct updated name only appears after the user manually refreshes the page. | This is a valid bug because even though the organization name is updated successfully in the system, the updated value is not immediately reflected in all parts of the application. After the update, some sections like other tabs and the dashboard header still show the old organization name. The correct updated name only appears after the user manually refreshes the page. |  | Medium | 1) Login as a User > Settings → Organisation 2) Change org name 3) Save > observe the result | Name updated. Reflected in dashboard header and billing page. | The organization name gets updated successfully; however, the updated name is not immediately reflected in other tabs or in the dashboard header. The changes only appear after performing a page refresh. | Dev | Shorya Kumar
59 | UB_059 | B_36 | This is a valid issue from a functional perspective because the user is trying to generate an API key but the system does not complete the action. Instead, it blocks the process and shows an upgrade message. | This is a valid issue from a functional perspective because the user is trying to generate an API key but the system does not complete the action. Instead, it blocks the process and shows an upgrade message. |  | High | 1) Login as a User > Settings → API Keys → Generate > Coyp Key | API key shown once. Copy prompt displayed. Key not shown again on reload. | The API key is not generated, and the system shows a message stating that API access is not available on the current plan and prompts the user to upgrade | Dev | Shorya Kumar
60 | UB_060 | B_37 | This is a valid issue because the system is not generating or displaying the API key as expected. When the user tries to access this feature, the process does not complete and no key (full or masked) is shown. Instead, the system only shows a message that API access is not available on the current plan and asks the user to upgrade. | This is a valid issue because the system is not generating or displaying the API key as expected. When the user tries to access this feature, the process does not complete and no key (full or masked) is shown. Instead, the system only shows a message that API access is not available on the current plan and asks the user to upgrade. |  | High | 1) Login as a User > Generate API key 2) Close/reload settings page 3) Check API keys section | Key not shown in full again. Only masked or last-4 shown. | The API key is not generated. Instead of showing the full key, the system does not provide any key and only displays a message about API access being unavailable on the current plan, prompting the user to upgrade. | Dev | Shorya Kumar
61 | UB_061 | B_38 | This is a valid issue because the support ticket works fine when no attachment is added, but fails when a file is attached. The system shows a “Failed to upload” error and does not create the ticket at all. This indicates that the attachment upload process is breaking the ticket submission flow. | This is a valid issue because the support ticket works fine when no attachment is added, but fails when a file is attached. The system shows a “Failed to upload” error and does not create the ticket at all. This indicates that the attachment upload process is breaking the ticket submission flow. |  | High | 1) Login as a User > Go to Support → New Ticket 2) Fill subject, category, priority, message 3) Submit > Observe the Result | Ticket created. Confirmation shown. Ticket appears in My Tickets list. | Support ticket gets created successfully when no attachment is added. However, if an attachment is included, the ticket submission fails and a “Failed to upload” error message is displayed, and the ticket is not created. | Dev | Shorya Kumar
62 | UB_062 | B_39 | This is a valid issue because the monitor name field does not enforce the expected 500-character limit. Users are able to enter more than 500 characters without any restriction or validation error. This shows that the input validation is missing or not working properly for this field. Ideally, the system should either stop users from entering extra characters or show a validation message when the limit is crossed. | This is a valid issue because the monitor name field does not enforce the expected 500-character limit. Users are able to enter more than 500 characters without any restriction or validation error. This shows that the input validation is missing or not working properly for this field. Ideally, the system should either stop users from entering extra characters or show a validation message when the limit is crossed. |  | Low | 1) Login as a User > Add Monitor > Enter 500 character monitor name 2. Save > Observe the Result | Either truncated cleanly or validation error. No database crash. | The monitor name field allows input of more than 500 characters and does not display any validation error message. | Dev | Shorya Kumar
63 | UB_063 | B_40 | On mobile view (375px), the landing page loads successfully, but there are noticeable UI issues. Some elements are not properly aligned and spacing is inconsistent. A few text sections are overflowing or breaking outside their containers, which disturbs the layout structure. Because of this, the content is not fully readable and the overall design looks unbalanced on smaller screens. The page is usable, but the responsiveness needs improvement to ensure proper alignment and better user experience on mobile devices. | On mobile view (375px), the landing page loads successfully, but there are noticeable UI issues. Some elements are not properly aligned and spacing is inconsistent. A few text sections are overflowing or breaking outside their containers, which disturbs the layout structure. Because of this, the content is not fully readable and the overall design looks unbalanced on smaller screens. The page is usable, but the responsiveness needs improvement to ensure proper alignment and better user experience on mobile devices. |  | High | 1) Open Chrome DevTools 2) Set viewport to 375×812 3) Scroll through entire page | No horizontal scroll. All text readable. Buttons tappable. Nav works. | The landing page loads properly on mobile view (375px), but there are UI alignment issues, and some text is overflowing or not properly aligned. | Dev | Shorya Kumar
64 | UB_064 | B_41 | This bug is created because it affects the basic usability of the application. Users expect actions to work on a single click, but needing multiple clicks creates confusion and frustration. It also indicates a problem with event handling or responsiveness. Since it impacts core functionality and user experience, it should be treated as a high-priority issue | This bug is created because it affects the basic usability of the application. Users expect actions to work on a single click, but needing multiple clicks creates confusion and frustration. It also indicates a problem with event handling or responsiveness. Since it impacts core functionality and user experience, it should be treated as a high-priority issue |  | High | 1) Open the website. 2) Navigate to any menu or clickable functionality. 3) Click on the menu/functionality once. 4) Observe the behavior. 5) If it does not open, click again (2–3 times). | Menu or functionality should open on a single click without delay. | Menu or functionality does not respond on the first click. When the user clicks once, there is no visible action or response from the system, which creates confusion. The user is then required to click the same menu or functionality multiple times (2–3 clicks) for it to finally open or execute. This indicates a delay or issue in click event handling, leading to poor user experience and inconsistent behavior across the application. | Dev | Shorya Kumar
65 | UB_065 | B_42 | This bug is reported because it directly affects the usability and accessibility of the application, especially on mobile devices. When UI elements are misaligned or distorted, users may struggle to understand or interact with the content properly. Additionally, if the menu does not open on clicking the icon, it blocks primary navigation, making it difficult for users to move through the application. Overall, this issue impacts core functionality and user experience, so it is a valid and high-priority defect. | This bug is reported because it directly affects the usability and accessibility of the application, especially on mobile devices. When UI elements are misaligned or distorted, users may struggle to understand or interact with the content properly. Additionally, if the menu does not open on clicking the icon, it blocks primary navigation, making it difficult for users to move through the application. Overall, this issue impacts core functionality and user experience, so it is a valid and high-priority defect. |  | High | 1) Open /dashboard on 375px viewport 2) Navigate through monitors, alerts, billing | All pages usable on mobile. No horizontal overflow. Buttons tappable. | The user interface appears broken or improperly aligned in certain sections. Clicking the menu icon does not open or display the menu. Navigation on mobile devices becomes challenging and not user-friendly. | Dev | Shorya Kumar
66 | UB_066 | B_43 | This issue is reported because it severely impacts the core usability of the application. When the sidebar menu does not open or is not visible, users are unable to access key navigation options, which blocks movement across different sections of the app. UI alignment issues further degrade the visual structure and make the interface confusing and difficult to use. Overall, this leads to a poor user experience and affects basic functionality, so it should be considered a high-priority defect. | This issue is reported because it severely impacts the core usability of the application. When the sidebar menu does not open or is not visible, users are unable to access key navigation options, which blocks movement across different sections of the app. UI alignment issues further degrade the visual structure and make the interface confusing and difficult to use. Overall, this leads to a poor user experience and affects basic functionality, so it should be considered a high-priority defect. |  | High | 1) Open /dashboard at 768px width | Layout adapts. Sidebar collapses or stacks correctly. | The sidebar menu is not opening or is not visible. Navigation options cannot be accessed by the user. There are issues with UI alignment across the interface. | Dev | Shorya Kumar
67 | UB_067 | B_44 | The subscription status message is not updating correctly based on the selected toggle option. When the user purchases a Yearly plan, the message “You are on this plan” is displayed correctly under the Yearly section. However, when the user switches the toggle to Monthly, the same message is still shown even though the user has not purchased the Monthly plan. This indicates that the UI is not properly reflecting the actual subscription state, leading to incorrect plan status being displayed to the user. | The subscription status message is not updating correctly based on the selected toggle option. When the user purchases a Yearly plan, the message “You are on this plan” is displayed correctly under the Yearly section. However, when the user switches the toggle to Monthly, the same message is still shown even though the user has not purchased the Monthly plan. This indicates that the UI is not properly reflecting the actual subscription state, leading to incorrect plan status being displayed to the user. |  | High | 1) Login as a User > Open the subscription/plans page. 2) Ensure the toggle is set to Yearly. 3) Verify the plan status message is displayed. 4) Switch the toggle to Monthly. 5) Observe the plan status message under the Monthly section | When Yearly is selected, the message should show “You are on this plan” for the Yearly plan only. When Monthly is selected, the message should update accordingly and should NOT incorrectly show “You are on this plan” if the user is not subscribed to Monthly. | The message “You are on this plan” is displayed even when the toggle is switched to Monthly, although the user has only purchased the Yearly plan. | Dev | Shorya Kumar
68 | UB_068 | B_45 | After successfully raising a support ticket, the user is correctly redirected to the support ticket list page. However, upon landing on the list page, the system automatically opens the details of the last created support ticket instead of displaying only the list view. This prevents the user from staying on the ticket list page and causes unintended navigation to the ticket detail screen. | After successfully raising a support ticket, the user is correctly redirected to the support ticket list page. However, upon landing on the list page, the system automatically opens the details of the last created support ticket instead of displaying only the list view. This prevents the user from staying on the ticket list page and causes unintended navigation to the ticket detail screen. |  | High | 1. Go to Support → New Ticket 2. Fill subject, category, priority, message 3. Submit | User should be redirected to the support ticket list page and only the list of tickets should be displayed. No ticket details should open automatically. | User is redirected to the list page, but the last created support ticket automatically opens in detail view. | Dev | Shorya Kumar
69 | UB_069 | B_46 | The “Settings” functionality is available in both the Profile section and the Side Menu, resulting in duplication of the same feature in two different locations. This creates inconsistency in the UI/UX and may confuse users about the correct place to access Settings. | The “Settings” functionality is available in both the Profile section and the Side Menu, resulting in duplication of the same feature in two different locations. This creates inconsistency in the UI/UX and may confuse users about the correct place to access Settings. |  | High | 1) Login to the application with valid credentials. | The “Settings” functionality should be available at only one defined location (either Profile section or Side Menu) as per the requirement/design to maintain consistency and avoid duplication. | The “Settings” functionality is available in both the Profile section and the Side Menu, allowing users to access the same feature from two different places. | Dev | Shorya Kumar
70 | UB_070 | B_47 | During the signup process, the magic link email is not being sent to the user’s registered email address. As a result, the user is unable to verify their account or complete the registration flow. This indicates a failure in the email delivery or authentication service integration. | During the signup process, the magic link email is not being sent to the user’s registered email address. As a result, the user is unable to verify their account or complete the registration flow. This indicates a failure in the email delivery or authentication service integration. |  | High | 1)Open browser (logged out) 2)Navigate to /signup 3)Enter a valid new email address 4)Click on Send Magic Link 5)Check the screen and inbox | Magic link email should be sent within 60 seconds | Error message displayed: “Failed to send magic link. Please try again.” | Dev | Shorya Kumar
71 | UB_071 | B_48 | The system is unable to validate or process the expired magic link because the magic link email is not being sent to the user during the signup process. As a result, the user does not receive the required verification email, making it impossible to test or handle the expired link scenario. This indicates a failure in the email delivery or authentication flow, affecting the overall signup and verification process. | The system is unable to validate or process the expired magic link because the magic link email is not being sent to the user during the signup process. As a result, the user does not receive the required verification email, making it impossible to test or handle the expired link scenario. This indicates a failure in the email delivery or authentication flow, affecting the overall signup and verification process. |  | High | 1)Open browser (logged out) 2)Navigate to login page 3)Enter a valid email 4)Click Send Magic Link | Magic link should be sent successfully After expiration (e.g., 1 hour), clicking the link should show: “Link expired” error message | Error message displayed: “Failed to send magic link. Please try again.” | Dev | Shorya Kumar
72 | UB_072 | B_49 | The magic link email is not being sent to the user during the signup process, due to which the user cannot receive or use the verification link. As a result, the validation flow for both active and expired magic links cannot be completed, impacting the account verification process and overall signup functionality. | The magic link email is not being sent to the user during the signup process, due to which the user cannot receive or use the verification link. As a result, the validation flow for both active and expired magic links cannot be completed, impacting the account verification process and overall signup functionality. |  | High | 1) In public page , scroll down to footer 2) click on status link after login | System should prevent duplicate subscriptions | No subscription flow accessible | Dev | Shorya Kumar
73 | UB_073 | B_50 | When a user attempts to sign up using an email address that already exists in the system, the application does not handle the error correctly. Instead of showing a clear and user-friendly message indicating that the email is already registered, the system displays an incorrect or unclear error response. This leads to confusion and poor user experience during the signup process. | When a user attempts to sign up using an email address that already exists in the system, the application does not handle the error correctly. Instead of showing a clear and user-friendly message indicating that the email is already registered, the system displays an incorrect or unclear error response. This leads to confusion and poor user experience during the signup process. |  | High | 1)Go to /signup 2)Enter an already registered email 3)Click Send Magic Link | Magic link should not be sent with proper error msg. | Generic error message displayed Magic link not sent Signup process blocked | Dev | Shorya Kumar
74 | UB_074 | B_51 | When the user clicks the Login button continuously more than 10 times, the system shows a “Too many requests” error message due to rate limiting. However, even after the user switches tabs or waits briefly and returns to the login page, a single click still continues to trigger the same “Too many requests” message. The system does not reset or recover quickly from the rate limit state, forcing the user to wait for an extended period before being able to log in normally again. | When the user clicks the Login button continuously more than 10 times, the system shows a “Too many requests” error message due to rate limiting. However, even after the user switches tabs or waits briefly and returns to the login page, a single click still continues to trigger the same “Too many requests” message. The system does not reset or recover quickly from the rate limit state, forcing the user to wait for an extended period before being able to log in normally again. |  | High | 1. Open the login page. > Click the Login button continuously more than 10 times rapidly | After the rate limit message is triggered, the system should recover after a short cooldown period. Once the user switches tabs or waits, a single login attempt should work normally without showing the “Too many requests” error again. | Even after switching tabs or returning to the page, a single click on the Login button still shows the “Too many requests” error. The user is unable to proceed until they wait for a long time or reset the session. | Dev | Shorya Kumar
75 | UB_075 | Bug_01_P8 | Footer Links Not Working – Unresponsive and 404 Errors | Footer Links Not Working – Unresponsive and 404 Errors |  | Medium | 1)Open the application (logged out / normal browser state) 2)Scroll to Footer section 3)Click each footer link one by one: Leaderboard Help Centre API Docs Status | All footer links should open correct and working pages | Leaderboard link is unresponsive (no action on click) Help Centre returns 404 error API Docs returns 404 error Status returns 404 error Footer navigation is broken | Dev | Sourav Naugain
76 | UB_076 | Bug_02_P7 | Landing Page UI Alignment Issues on Mobile View (375px) | Landing Page UI Alignment Issues on Mobile View (375px) |  | Medium | 1)Open Chrome browser 2)Enable Developer Tools 3)Set device toolbar to 375 × 812 (mobile view) 4)Open the Landing Page 5)Scroll through the entire page | Landing page should be fully responsive on 375px mobile view No text overflow or layout breaking All elements should be properly aligned | Landing page should be fully responsive on 375px mobile view No text overflow or layout breaking All elements should be properly aligned | Dev | Sourav Naugain
77 | UB_077 | Bug_03_B1 | Blog Page Images Not Loading & “Load More Articles” Button Not Working Properly | Blog Page Images Not Loading & “Load More Articles” Button Not Working Properly |  | High | 1)Open the application 2)Navigate to /blog page 3)Observe the list of blog posts 4)Check if feature images are loading 5)Click on “Load More Articles” button | Blog post images should be properly displayed “Load More Articles” button should load additional posts dynamically Page should not redirect to top unnecessarily | Blog page loads successfully and posts are visible Images are not visible/loading “Load More Articles” button does not load more posts Button click redirects user to top of the page instead of fetching additional articles | Dev | Sourav Naugain
78 | UB_078 | Bug_04_SP_01 | Public Status Page Not Accessible (Redirects to Login / 404 Error) | Public Status Page Not Accessible (Redirects to Login / 404 Error) |  | High | 1) In public page , scroll down to footer 2) click on status link after login | Status page should load publicly without login Monitor list and uptime bars should be visible | Logged out → redirected to Sign In Logged in → 404 error | Dev | Sourav Naugain
79 | UB_079 | Bug_05_SP_02 | “All Systems Operational” Banner Not Displayed | “All Systems Operational” Banner Not Displayed |  | Medium | 1) In public page , scroll down to footer 2) click on status link after login | “All systems operational” message should be shown when all monitors are up | Banner not displayed Page redirects or shows 404 | Dev | Sourav Naugain
80 | UB_080 | Bug_06_SP_03 | Active Incident Not Displayed on Status Page | Active Incident Not Displayed on Status Page |  | High | 1) In public page , scroll down to footer 2) click on status link after login | Active incidents should be displayed with title, time, and timeline | No incident details visible Redirect/404 instead of data | Dev | Sourav Naugain
81 | UB_081 | Bug_07_SP_04 | Uptime Time Range Selector Not Functional | Uptime Time Range Selector Not Functional |  | Medium | 1) In public page , scroll down to footer 2) click on status link after login | Uptime bars should update based on selected time range | No interaction possible Page not accessible | Dev | Sourav Naugain
82 | UB_082 | Bug_08_SP_05 | Status Page Email Subscription Not Working | Status Page Email Subscription Not Working |  | Medium | 1) In public page , scroll down to footer 2) click on status link after login | User should be able to subscribe via email successfully | No subscription form accessible No confirmation message | Dev | Sourav Naugain
83 | UB_083 | Bug_09_SP_06 | Invalid Email Validation Not Verifiable in Subscription | Invalid Email Validation Not Verifiable in Subscription |  | Medium | 1) In public page , scroll down to footer 2) click on status link after login | Invalid email should show validation error | No validation possible Page not reachable | Dev | Sourav Naugain
84 | UB_084 | Bug_12_A_01 | Magic Link Email Not Sent During Signup | Magic Link Email Not Sent During Signup |  | High | 1)Open browser (logged out) 2)Navigate to /signup 3)Enter a valid new email address 4)Click on Send Magic Link 5)Check the screen and inbox | Magic link email should be sent within 60 seconds | Error message displayed: “Failed to send magic link. Please try again.” | Dev | Sourav Naugain
85 | UB_085 | Bug_13_A_03 | Magic Link Login Not Working Due to Email Not Being Sent | Magic Link Login Not Working Due to Email Not Being Sent |  | High | 1)Open browser (logged out) 2)Go to Login 3)Enter a valid email address 4)Click on Send Magic Link | Magic link email should be sent successfully | Error message displayed: “Failed to send magic link. Please try again.” | Dev | Sourav Naugain
86 | UB_086 | Bug_15_A_06 | Magic Link Not Sent for Unregistered Email | Magic Link Not Sent for Unregistered Email |  | High | 1)Open browser (logged out) 2)Navigate to login page 3)Enter a unregistered email 4)Click Send Magic Link | Magic link should not be sent for unregistered mail | Magic link not sent Error message displayed | Dev | Sourav Naugain
87 | UB_087 | Bug_16_A_07 | Incorrect Error Handling When Signing Up with Existing Email | Incorrect Error Handling When Signing Up with Existing Email |  | Medium | 1)Go to /signup 2)Enter an already registered email 3)Click Send Magic Link | Magic link should not be sent with proper error msg. | Generic error message displayed Magic link not sent Signup process blocked | Dev | Sourav Naugain
88 | UB_088 | Bug_17_M_02 | SSL Expiry Date Not Displayed on Monitor Detail Page | SSL Expiry Date Not Displayed on Monitor Detail Page |  | Medium | 1)Login as a valid user 2)Go to New Monitor 3)Select SSL monitor type 4)Enter domain (without https://) 5)Click Save | Monitor should be created successfully SSL expiry date should be displayed on the detail page | Monitor is created and visible in the system SSL expiry date is not shown on the detail page | Dev | Sourav Naugain
89 | UB_089 | Bug_19_M_08 | Heartbeat URL Not Generated or Displayed After Monitor Creation | Heartbeat URL Not Generated or Displayed After Monitor Creation |  | High | 1)Login as a valid user 2)Go to New Monitor 3)Select Heartbeat monitor type 4)Enter monitor name 5)Click Save | Monitor should be created successfully A unique heartbeat URL should be generated and shown on the detail page | Monitor is created and visible in the system Unique heartbeat URL is not generated or displayed | Dev | Sourav Naugain
90 | UB_090 | Bug_20_M_10 | Invalid URL Accepted While Creating HTTP Monitor | Invalid URL Accepted While Creating HTTP Monitor |  | High | 1)Go to "New Monitor" 2)Select HTTP type 3)Enter notaurl in the URL field 4)Click on Save | System should show a validation error indicating invalid URL format and prevent monitor creation. | System accepts the invalid URL without any validation error. Monitor is successfully created with incorrect input. | Dev | Sourav Naugain
91 | UB_091 | Bug_21_I_01 | Incident appears when monitor goes down | Incident appears when monitor goes down |  | Medium | 1. Put a monitor into Down state 2. Go to Incidents page | New incident listed with monitor name, start time, duration counting up. | This test case verifies whether an incident is triggered when a monitor goes into a Down state. However, during testing, the monitor could not be forced into a Down state due to environment limitations or stable endpoint behavior. As a result, the incident creation scenario could not be validated. | Dev | Sourav Naugain
92 | UB_092 | Bug_22_I_02 | Incident resolves when monitor recovers | Incident resolves when monitor recovers |  | High | 1. Have an open incident 2. Make monitor recover 3. Check incidents list | Incident shows as Resolved with end time and total duration. | This test case depends on an already active/open incident. Since the monitor did not go into a Down state, no incident was generated. Therefore, the recovery flow and incident resolution could not be tested. | Dev | Sourav Naugain
93 | UB_093 | Bug_21_I_03 | Incident history preserved | Incident history preserved |  | Medium | 1. View Incidents page 2. Check past resolved incidents | Historical incidents listed with start, end, duration, affected monitor. | This test case requires previously resolved incidents to validate historical data. As no incidents were triggered during testing, there was no historical data available to verify this functionality. | Dev | Sourav Naugain
94 | UB_094 | Bug_22_I_04 | Incident detail page | Incident detail page |  | High | 1. Click on any incident | Timeline shown. Affected monitor name. Duration. Status updates. | This test case requires an existing incident to validate detailed information such as timeline, duration, and status updates. Since no incident was generated, the incident detail view could not be accessed or tested. | Dev | Sourav Naugain
95 | UB_095 | Bug_23_AL_10 | Alert with invalid webhook URL | Alert with invalid webhook URL |  | High | 1)Create a webhook channel 2)Enter notaurl as the URL 3)Click on Save | System should display a validation error for invalid URL format and prevent saving the webhook channel. | Webhook channel is created successfully even when an invalid URL is provided. No validation message or error is displayed to the user. | Dev | Sourav Naugain
96 | UB_096 | Bug_24_R_04 | Monthly Report Limit Not Enforced for Builder Plan | Monthly Report Limit Not Enforced for Builder Plan |  | High | 1)Log in as a Builder plan user 2)Generate 1 report (should succeed) 3)ttempt to generate a second report within the same month | System should block the second report generation. A limit message or upgrade prompt should be displayed to the user. | Second report is generated successfully without any restriction. No limit enforcement or upgrade prompt is shown, and the report is accessible. | Dev | Sourav Naugain
97 | UB_097 | Bug_25_BL_02 | Monthly toggle works in billing | Monthly toggle works in billing |  | High | 1. Go to billing page 2. Click Monthly / Annual toggle | Prices update for GBP plans. Annual shows savings %. | GBP pricing updates correctly, but annual savings % is not displayed. | Dev | Sourav Naugain
98 | UB_098 | Bug_26_BL_03 | Invoice appears after payment | Invoice appears after payment |  | Medium | 1. Complete a Stripe payment 2. Check billing page invoices section | Invoice listed with date, amount, plan name. | Invoice shows date and amount, but plan name is missing. | Dev | Sourav Naugain
99 | UB_099 | Bug_27_BL_04 | View invoice PDF | View invoice PDF |  | High | 1. Click on an invoice in billing history | Stripe invoice PDF opens in new tab. | Invoice PDF opens in the same tab instead of a new tab. | Dev | Sourav Naugain
100 | UB_100 | Bug_28_BL_05 | Cancel subscription | Cancel subscription |  | Medium | 1. Go to billing (on paid plan) 2. Click Cancel Plan 3. Confirm | Subscription set to cancel at period end. Access continues until then. | Subscription does not cancel. Status and access remain unchanged. | Dev | Sourav Naugain
101 | UB_101 | Bug_29_BL_06 | Access continues after cancel request | Access continues after cancel request |  | High | 1. Cancel subscription 2. Check plan features still accessible 3. Check billing page | Shows cancellation date. Features still accessible until period end. | Cancellation date not applied correctly. Subscription remains active. | Dev | Sourav Naugain
102 | UB_102 | Bug_29_BL_07 | Failed payment — subscription marked past_due | Failed payment — subscription marked past_due |  | High | 1. Use Stripe test card: 4000 0000 0000 9995 2. Complete checkout | Payment fails. Subscription status shows as past_due. User notified. | Payment fails with invalid card error. Transaction not completed. | Dev | Sourav Naugain
103 | UB_103 | Bug_30_BL_13 | Razorpay Payment Fails with Valid Test Card | Razorpay Payment Fails with Valid Test Card |  | High | 1)In Razorpay modal use test card: 4111 1111 1111 1111 2)Enter any future expiry and any CVV 3)Complete the payment | User should be redirected to the dashboard. Plan should be activated and subscription entry should be created in DB with status active. | Payment is not completed. An error message "Card not supported" is displayed, and the user is neither redirected nor subscribed. | Dev | Sourav Naugain
104 | UB_104 | Bug_31_BL_15 | Razorpay Subscription Cancellation Not Working | Razorpay Subscription Cancellation Not Working |  | High | 1)Go to billing page 2)Click Cancel 3)Confirm cancellation (two-step process) | Subscription should be cancelled. Plan should revert to Free at the end of the current billing period. | Subscription remains active even after attempting cancellation. Plan does not switch back to the Free tier at the end of the billing cycle. | Dev | Sourav Naugain
105 | UB_105 | Bug_32_S_01 | Update organisation name | Update organisation name |  | High | 1. Settings → Organisation 2. Change org name 3. Save | Name updated. Reflected in dashboard header and billing page. | Name updates successfully but not reflected across tabs until refresh. | Dev | Sourav Naugain
106 | UB_106 | Bug_33_S_03 | Generate API key | Generate API key |  | Medium | 1. Settings → API Keys → Generate 2. Copy key | API key shown once. Copy prompt displayed. Key not shown again on reload. | API key is not generated; message shown: API access not available on plan. | Dev | Sourav Naugain
107 | UB_107 | Bug_34_S_04 | API key shown once only | API key shown once only |  | High | 1. Generate API key 2. Close/reload settings page 3. Check API keys section | Key not shown in full again. Only masked or last-4 shown. | API key is not generated; system shows API access not available message. | Dev | Sourav Naugain
108 | UB_108 | Bug_35_S_05 | Invite team member | Invite team member |  | High | 1. Settings → Team → Invite 2. Enter email address 3. Send invite | Invite email sent to recipient. | Functionality not exists. | Dev | Sourav Naugain
109 | UB_109 | Bug_36_S_06 | Accept team invite | Accept team invite |  | High | 1. Open invite email 2. Click acceptance link | Invited user joins org. Lands on dashboard. Sees same monitors. | Functionality not exists. | Dev | Sourav Naugain
110 | UB_110 | Bug_37_S_07 | Team member invite blocked on Free plan | Team member invite blocked on Free plan |  | Medium | 1. Free plan user → Settings → Team → Invite | Blocked. Solo plan only — upgrade prompt shown. | Functionality not exists. | Dev | Sourav Naugain
111 | UB_111 | Bug_39_SU_01 | Submit support ticket | Submit support ticket |  | High | 1. Go to Support → New Ticket 2. Fill subject, category, priority, message 3. Submit | Ticket created. Confirmation shown. Ticket appears in My Tickets list. | Ticket works without attachment, but fails when attachment is added with "Failed to upload" error and ticket is not created. | Dev | Sourav Naugain
112 | UB_112 | Bug_40_SEC_05 | Dashboard on mobile (375px) | Dashboard on mobile (375px) |  | Medium | 1. Open /dashboard on 375px viewport 2. Navigate through monitors, alerts, billing | All pages usable on mobile. No horizontal overflow. Buttons tappable. | UI is distorted/misaligned. Menu not opening or visible. Navigation difficult. | Dev | Sourav Naugain
113 | UB_113 | Bug_42_SEC_08 | Long input values handled | Long input values handled |  | Medium | 1. Enter 500 character monitor name 2. Save | Either truncated cleanly or validation error. No database crash. | Monitor name accepts more than 500 characters without validation error. | Dev | Sourav Naugain
114 | UB_114 | Bug_43 | Unresponsive Click Requires Multiple Attempts | Unresponsive Click Requires Multiple Attempts |  | Medium | 1)OPEN site 2) click on any buttons, menus icons profile icon etc. | Single click should reliably trigger the intended action immediately. | Sometimes the first click is not registered, and the user has to click multiple times for the action to work. | Dev | Sourav Naugain
115 | UB_115 | Bug_44 | Login/Logout state incorrectly synced across multiple tabs | Login/Logout state incorrectly synced across multiple tabs |  | High | 1)Open the application in Tab 1 and Tab 2 2)In Tab 1, log in with a valid account 3)Observe Tab 2 without refresh 4)Now log out from Tab 1 5)Observe Tab 2 again | Each tab should maintain independent session state until refresh or explicit sync. Login/logout actions should only affect the active tab or should be handled with proper session synchronization (controlled behavior). | When user logs in on one tab, other open tabs automatically reflect logged-in state without refresh When user logs out from one tab, other tabs also get logged out automatically Session state is mirrored across tabs unexpectedly | Dev | Sourav Naugain
116 | UB_116 | BUG01_P01 | 2 issue on console | 2 issue on console | Landing page loads | p1 | 1.Open Chrome Browser 2.hit url"https://dev.uptrue.io/" 3.Browser open. Not logged in. 4. Check console for errors | Page loads completely. No broken images. No JS console errors. | 1.A form field element should have an id or name attribute 2.Content Security Policy of your site blocks the use of 'eval' in JavaScript` | Dev | Kriti chawla
117 | UB_117 | BUG02_P03 | INR simulation missing | INR simulation missing | INR monthly pricing correct | p1 | 1.Open Chrome Browser 2.hit url"https://dev.uptrue.io/" 3.Browser open. Not logged in. 4.GO TO Pricing tab.5.Simulate Indian user (or check INR tab) | INR simulation button must be there | Simulate Indian user (or check INR tab) missing | Dev | Kriti chawla
118 | UB_118 | BUG03_P04 | View landing as UK user not found | View landing as UK user not found | GBP pricing correct | p1 | 1.Open Chrome Browser 2.hit url "https://dev.uptrue.io/" 3.Browser open. Not logged in. 4.GO TO Pricing tab. 5.View landing as UK user 6. Check all plan prices in £ | View landing as UK user | No option for View landing as UK user found | Dev | Kriti chawla
119 | UB_119 | BUG04_P06 | 2 console issues found | 2 console issues found | CTA buttons navigate to signup | p1 | 1.Open Chrome Browser 2.hit url "https://dev.uptrue.io/" 3.Browser open. Not logged in. 4.GO TO Pricing tab. 5. Click "Start Free" | it should work . | 1.An element doesn't have an autocomplete attribute2.Content Security Policy of your site blocks the use of 'eval' in JavaScript` | Dev | Kriti chawla
120 | UB_120 | BUG05_B02 | uptrue and start monitoring Hyperlinks not working on every page. | uptrue and start monitoring Hyperlinks not working on every page. | Blog post opens correctly | p1 | 1.Open Chrome Browser 2.hit url "https://dev.uptrue.io/" 3.Browser open. Not logged in. 4. Click any blog post 5. Read through content | uptrue and start monitoring Hyperlinks should work. | uptrue and start monitoring Hyperlinks not working on every page.No page found screen occurs. | Dev | Kriti chawla
121 | UB_121 | BUG06_A01 | signup failed | signup failed | Sign up with email (magic link) | p1 | 1.Open Chrome Browser 2.hit url "https://dev.uptrue.io/"3. Go to /signup 4. Enter a new email address 5. Click Send Magic Link 6. Check inbox | Failed to send magic link. Please try again. | sometimes found | Dev | Kriti chawla
122 | UB_122 | BUG08_A04 | signup page occurred.link expired screen not occurred. | signup page occurred.link expired screen not occurred. | Expired magic link rejected | p1 | 1.Open Chrome Browser 2.hit url "https://dev.uptrue.io/"3.Go to /signup 4. create a newsign up. 5. Request magic link 6. Wait more than 1 hour 7. Click the link | Error message shown: link expired. Not logged in. No crash | signup page occurred.link expired screen not occurred. | Dev | Kriti chawla
123 | UB_123 | BUG09_M10 | Http type monitor created with "notaurl" text successfully | Http type monitor created with "notaurl" text successfully | Create with invalid URL | p1 | 1.Open Chrome Browser 2.hit url "https://dev.uptrue.io/" 3.Go to /signup1. New monitor → HTTP type 4. Enter "notaurl" in URL field 5. Save | Validation error: invalid URL format. | Http type monitor created with "notaurl" text successfully | Dev | Kriti chawla
124 | UB_124 | BUG10_M11 | Alert message not matching. | Alert message not matching. | SSRF — private IP blocked | p1 | 1.Open Chrome Browser 2.hit url "https://dev.uptrue.io/" 3.Go to /signin 4. New monitor → HTTP type 5. Enter http://192.168.1.1 6.. Save | Error: Monitor target URL is not permitted. | Private or localhost URLs cannot be monitored | Dev | Kriti chawla
125 | UB_125 | BUG13_PL04 | Upgrade prompt shown on creating 1st status page. | Upgrade prompt shown on creating 1st status page. | Free: 1 status page only | p1 | 1.Open Chrome Browser 2.hit url "https://dev.uptrue.io/" 3.Logged in as Free plan user unless stated. 4.Free user creates 1st status page 5.Observe | 1st status page must be created | Status pages are not available on your current plan. Upgrade to unlock this feature. | Dev | Kriti chawla
126 | UB_126 | BUG14_PL05 | Able to create reports using Free user plan. | Able to create reports using Free user plan. | Free: no AI reports | p1 | 1.Open Chrome Browser 2.hit url "https://dev.uptrue.io/" 3.Logged in as Free plan user unless stated. 4. Free user → Reports → New 5.Observe | Blocked. Upgrade prompt shown. | Able to create reports using free user plan. | Dev | Kriti chawla
127 | UB_127 | BUG15_PL07 | unable to create status page in Lite plan. | unable to create status page in Lite plan. | Limits lifted after upgrade | p1 | 1.Open Chrome Browser 2.hit url "https://dev.uptrue.io/" 3. Upgrade Free → Lite or higher 4. Retry previously blocked action4.Try to create 1st status page 5.Observe | status page must be craeted | Status pages are not available on your current plan. Upgrade to unlock this feature. | Dev | Kriti chawla
128 | UB_128 | BUG16_BL13 | Card not supported | Card not supported | Complete Razorpay payment | p1 | 1.Open Chrome Browser 2.hit url "https://dev.uptrue.io/" 3.Logged in. On billing/settings page. 4. In Razorpay modal use test card: 4111 1111 1111 1111 5. Any future expiry, any CVV 6. Complete payment | Redirected to dashboard. Plan activated. Subscription row in DB with status: active. | card not supported. | Dev | Kriti chawla
129 | UB_129 | BUG17_SPA04 | Failed to create status page | Failed to create status page | Duplicate slug rejected | p1 | 1.Open Chrome Browser 2.hit url "https://dev.uptrue.io/" 3.Logged in. At least one monitor exists. 4. Create status page with slug "my-status" 5.. Try to create another with same slug "my-status" | Validation error: slug already in use. | Failed to create status page | Dev | Kriti chawla